## Projects
No. | Title | Project Proponent | Project Portfolio Manager | Project Manager | Start Date | End Date | Status | Progress | Is external project? | Has implementation plan? | Latest Check-in By | Latest Check-in When | Latest Check-in
145 | Trasol Exctive Interface Appliction | Meshari Almotairi | Sultan Alfaifi | Abdulrahman Algharib (SMP), Kholoud Alhwaiti (SMP), Mohammed Alanazi | 2025-06-01 | 2025-11-01 | In Progress | 95.00% | No | No | Abdulrahman Algharib (SMP) | 2025-10-14 10:04 | Brief: Development of the Executive App has been completed, with final steps now focused on resolving signature integration responsibilities. Development Completion & Signature Integration: All additional features have been successfully implemented, and the Executive App is now ready for use. The integration with the digital signature solution is still pending and currently with (T&D) team. A meeting is scheduled this week to decide whether T&D will lead the integration with Signit, or if GA will proceed directly to close the project. Action Points: 1- Hold meeting with T&D to finalize ownership of signature integration. 2- Proceed with integration based on agreed lead. 3- Close project following successful deployment.
128 | Seascape Counsil | Sultan Alfaifi | Sultan Alfaifi | Abdulrahman Algharib (SMP), Ayedh Althobaiti, Kholoud Alhwaiti (SMP) | 2024-07-01 | 2026-01-01 | On Hold | 72.00% | No | No | Abdulrahman Algharib (SMP) | 2025-09-30 11:02 | On Hold due to restructuring across NEOM.
125 | Demolishing App | Ammar Awan, Ayedh Althobaiti | Sultan Alfaifi | Abdulrahman Algharib (SMP), Ammar Awan, Ayedh Althobaiti, Kholoud Alhwaiti (SMP) | 2025-06-19 | 2025-12-01 | In Progress | 90.00% | No | No | Kholoud Alhwaiti (SMP) | 2025-10-14 11:01 | Brief: Significant development progress has been made on the Demolishing App, with the first prototype completed and PMO support continuing across all phases. This phase focused on enhancing the user journey and structuring the workflow in line with the updated project direction. 1- Prototype Completion & Application Enhancements: The initial prototype of the Demolishing App is now ready. In parallel, several enhancements were introduced to the user interface, improving usability and aligning the application with operational needs. The user journey was reviewed and updated based on the revised application scope. 2- Workflow Development – Process Structuring: The team is now working on defining the workflow for demolition requests. The focus is on automation and process clarity, which will improve turnaround time and transparency during request handling. 3- Stakeholder Coordination – Workflow Alignment: Coordination is ongoing with all relevant stakeholders to design the workflow in line with the new organizational structure. The goal is to clearly define roles and responsibilities, ensuring a smooth and aligned rollout during implementation. Action Points: Finalize workflow structure in coordination with stakeholders. Conduct internal testing of the prototype.
119 | Permits and Licenses Phase 2 | Meshari Almotairi | Yasir Alharbi | Abdulrahman Algharib (SMP), Tamer Almadani | 2025-05-25 | 2025-11-01 | In Progress | 45.00% | No | No | Abdulrahman Algharib (SMP) | 2025-10-14 09:57 | 1. GAP Analysis – Report Submission & Review: GAP Analysis report was officially received from Jacobs on October 7, and a review meeting was held to discuss key findings and recommendations. 2. Clinic Licensing – Saudi Business Center Letter: NEOM received a formal letter from SBC, requesting NEOM to implement internal recommendations and resolve key issues before Riyadh Municipality and SBC can proceed with issuing operational licenses. 3. CEO/Board Presentation – Updates and Finalization: Several adjustments were made to the presentation intended for the NEOM Board. The updated version is currently under review and is expected to be finalized and approved within this week. Action Points: 1- Coordinate internally to address issues raised by the Saudi Business Center. 2- Finalize and approve the updated Board presentation.
103 | Register Coral Reefs in Saudi Waters on The World Natural Heritage List with UNESCO | Miaad Alharbi, Sultan Alfaifi | Sultan Alfaifi | Abdulrahman Algharib (SMP), Ammar Awan, Kholoud Alhwaiti (SMP) | 2024-07-01 | 2026-08-29 | In Progress | 65.00% | No | No | Kholoud Alhwaiti (SMP) | 2025-10-14 11:04 | Brief: Progress continues on the Registering Coral Reefs in Saudi Waters on the World Natural Heritage List with UNESCO project, in collaboration with the National Committee and the Nature team. The focus this week was on preparing for the upcoming UNESCO delegation visit and finalizing documentation with NCW. Topic 1: Coordination Meeting and Upcoming UNESCO Delegation Visit 1- A coordination meeting was held last Thursday between NEOM, the Nature team, the National Committee, and the National Community to discuss the upcoming UNESCO delegation visit scheduled for October 18–23. 2- The planned visit agenda is as follows: October 18: Meeting in Riyadh. October 19: Site visit to NEOM (Sharma and Lazour areas). October 20: Meeting with HRH the Governor of Tabuk Region, followed by a presentation session on the project and site management plan. 3- The draft Site Management Plan was received from NCW for NEOM’s review. NEOM reviewed the document, incorporated additional inputs and revisions, and has now sent the updated version back to NCW for their consideration. Action Points: 1- Follow up with NCW regarding feedback on the revised Site Management Plan. 2- Finalize preparations for the UNESCO delegation visit (October 18–23). 3- Coordinate with stakeholders to ensure alignment on visit agenda, logistics, and presentation content.