## Check-in History
Project No. | Project Title | Checked-in By | Checked-in When | Checked-in Update
125 | Demolishing App | Kholoud Alhwaiti (SMP) | 2025-10-14 11:01 | Brief: Significant development progress has been made on the Demolishing App, with the first prototype completed and PMO support continuing across all phases. This phase focused on enhancing the user journey and structuring the workflow in line with the updated project direction. 1- Prototype Completion & Application Enhancements: The initial prototype of the Demolishing App is now ready. In parallel, several enhancements were introduced to the user interface, improving usability and aligning the application with operational needs. The user journey was reviewed and updated based on the revised application scope. 2- Workflow Development – Process Structuring: The team is now working on defining the workflow for demolition requests. The focus is on automation and process clarity, which will improve turnaround time and transparency during request handling. 3- Stakeholder Coordination – Workflow Alignment: Coordination is ongoing with all relevant stakeholders to design the workflow in line with the new organizational structure. The goal is to clearly define roles and responsibilities, ensuring a smooth and aligned rollout during implementation. Action Points: Finalize workflow structure in coordination with stakeholders. Conduct internal testing of the prototype.
145 | Trasol Exctive Interface Appliction | Abdulrahman Algharib (SMP) | 2025-10-14 10:04 | Brief: Development of the Executive App has been completed, with final steps now focused on resolving signature integration responsibilities. Development Completion & Signature Integration: All additional features have been successfully implemented, and the Executive App is now ready for use. The integration with the digital signature solution is still pending and currently with (T&D) team. A meeting is scheduled this week to decide whether T&D will lead the integration with Signit, or if GA will proceed directly to close the project. Action Points: 1- Hold meeting with T&D to finalize ownership of signature integration. 2- Proceed with integration based on agreed lead. 3- Close project following successful deployment.
119 | Permits and Licenses Phase 2 | Abdulrahman Algharib (SMP) | 2025-10-14 09:57 | 1. GAP Analysis – Report Submission & Review: GAP Analysis report was officially received from Jacobs on October 7, and a review meeting was held to discuss key findings and recommendations. 2. Clinic Licensing – Saudi Business Center Letter: NEOM received a formal letter from SBC, requesting NEOM to implement internal recommendations and resolve key issues before Riyadh Municipality and SBC can proceed with issuing operational licenses. 3. CEO/Board Presentation – Updates and Finalization: Several adjustments were made to the presentation intended for the NEOM Board. The updated version is currently under review and is expected to be finalized and approved within this week. Action Points: 1- Coordinate internally to address issues raised by the Saudi Business Center. 2- Finalize and approve the updated Board presentation.
119 | Permits and Licenses Phase 2 | Abdulrahman Algharib (SMP) | 2025-10-07 09:07 | Brief: Key activities progressed over the past two weeks across the GAP analysis, clinic licensing, and Board presentation tracks. 1- Jacobs – GAP Analysis & Stakeholder Engagement: Work is underway with Jacobs to finalize Stage 2, with the GAP Analysis report expected between November 13–17. Stage 3 (Stakeholder Engagement) is also scheduled to begin on November 13. 2- Clinic Licensing – Submission to Riyadh Municipality: Clinic licensing requests were submitted to Riyadh Municipality after fulfilling additional requirements needed for permit processing. 3- Board Presentation – CEO Review: BoD presentation has been finalized and will be shared with the CEO for approval before presenting to the Board. Action Points: 1- Finalize GAP Analysis with Jacobs. 2- Track clinic licensing status. 3- Present to CEO for review.
145 | Trasol Exctive Interface Appliction | Mohammed Alanazi | 2025-09-30 12:08 | The Executive App development has been completed, and it is ready to be used by the GA management. The integration activates with the signature solution is currently with T&D Team.
128 | Seascape Counsil | Abdulrahman Algharib (SMP) | 2025-09-30 11:02 | On Hold due to restructuring across NEOM.
119 | Permits and Licenses Phase 2 | Abdulrahman Algharib (SMP) | 2025-09-16 09:18 | Brief: Work is ongoing with Jacobs and Riyadh Region Municipality to address regulatory gaps and clinic licensing challenges. Jacobs Coordination – Gap Analysis: Several meetings were held with Jacobs to review and analyze existing permitting gaps. Analysis is still in progress. Riyadh Municipality – Clinic Licensing Solutions: A meeting was held with Riyadh Municipality to discuss the 5 medical clinics. Proposed solutions were presented and have been shared with the CEO. A presentation is now being prepared for the Board of Directors. Action Points: 1- Finalize gap analysis with Jacobs. 2- Complete BoD presentation based on municipal proposals.
128 | Seascape Counsil | Abdulrahman Algharib (SMP) | 2025-09-15 15:20 | On Hold due to restructuring across NEOM.
145 | Trasol Exctive Interface Appliction | Abdulrahman Algharib (SMP) | 2025-09-15 15:10 | Project Overview: This week, progress continued on the ongoing development of the platform, with new features and enhancements added based on requirements from the President’s Office. The project is also under review by NEOM Tech & Digital, marking an important step in its evaluation and future integration. Topic 1: Feature Enhancements Additional functionalities were implemented based on the CEO Office requests, including an interactive dashboard and user interface improvements. Topic 2: Engagement with NEOM Tech & Digital The project has now been taken under evaluation by NEOM Tech & Digital During the recent meeting, the company (Signit) requested details from NEOM regarding the number of users for the platform and other technical requirements to prepare their proposal. Communication with Signit is ongoing to enable access integration, and coordination is currently being handled directly through Tech & Digital. Action Points: 1- Provide Signet with the requested No. of users and platform details in order to send the proposal 2- Continue coordination between Signet and Tech & Digital for access integration. 3- Review and align with Tech & Digital’s evaluation and proposal requirements. 4- Monitor new feature performance (dashboard & UI enhancements) to ensure alignment with CEO expectations.
125 | Demolishing App | Kholoud Alhwaiti (SMP) | 2025-09-15 15:04 | Brief: Initial structuring and stakeholder engagement for the Demolishing App project has been completed, with PMO officially supporting the project across all stages. 1- Project Structuring – Phases and Roadmap: The project was structured into defined phases, and a comprehensive roadmap and execution plan were developed in coordination with the project manager. This structure will guide project delivery and tracking. 2- User Journey Design – Application Experience: A user experience map was designed to guide how users will interact with the Demolishing App. This ensures the solution is intuitive and aligned with operational requirements. 3- Stakeholder Alignment – Roles and Benefits: All relevant stakeholders and beneficiary parties were identified and briefed on their roles in the project. Their input will be critical for both implementation and ongoing system usage Action Points: 1- Continue PMO support across all phases. 2- Finalize documentation of roadmap and user journey. 3- Conduct next meeting to update and refine project planning.
145 | Trasol Exctive Interface Appliction | Kholoud Alhwaiti (SMP) | 2025-09-07 14:50 | Project Overview: This week, progress continued on the ongoing development of the platform, with new features and enhancements added based on requirements from the President’s Office. The project is also under review by NEOM Tech & Digital, marking an important step in its evaluation and future integration. Topic 1: Feature Enhancements Additional functionalities were implemented based on the President’s Office requests, including an interactive dashboard and user interface improvements. Topic 2: Engagement with NEOM Tech & Digital The project has now been taken under evaluation by NEOM Tech & Digital During the recent meeting, the company requested details from NEOM regarding the number of users for the platform and other technical requirements to prepare their proposal. Communication with Sinet is ongoing to enable access integration, and coordination is currently being handled directly through Tech & Digital. Action Points: Provide Signet with the requested No. of users and platform details in order to send the proposal Continue coordination between Signet and Tech & Digital for access integration. Review and align with Tech & Digital’s evaluation and proposal requirements. Monitor new feature performance (dashboard & UI enhancements) to ensure alignment with CEO expectations.
145 | Trasol Exctive Interface Appliction | Kholoud Alhwaiti (SMP) | 2025-09-07 14:49 | Project Overview: This week, progress continued on the ongoing development of the platform, with new features and enhancements added based on requirements from the President’s Office. The project is also under review by NEOM Tech & Digital, marking an important step in its evaluation and future integration. Topic 1: Feature Enhancements Additional functionalities were implemented based on the President’s Office requests, including an interactive dashboard and user interface improvements. Topic 2: Engagement with NEOM Tech & Digital The project has now been taken under evaluation by NEOM Tech & Digital During the recent meeting, the company requested details from NEOM regarding the number of users for the platform and other technical requirements to prepare their proposal. Communication with Sinet is ongoing to enable access integration, and coordination is currently being handled directly through Tech & Digital. Action Points: Provide Signet with the requested No. of users and platform details in order to send the proposal Continue coordination between Signet and Tech & Digital for access integration. Review and align with Tech & Digital’s evaluation and proposal requirements. Monitor new feature performance (dashboard & UI enhancements) to ensure alignment with CEO expectations.
119 | Permits and Licenses Phase 2 | Abdulrahman Algharib (SMP) | 2025-09-03 15:18 | Brief: Progress has been made on several organizational and strategic fronts over the past two weeks, including coordination with government entities, preparation of official correspondence, and the launch of a new consultancy project. Topic 1: Health Asset Licensing – Coordination with the Saudi Business Center Coordination took place with the Saudi Business Center regarding the licensing of health assets. All assets have been received by Riyadh Municipality, which has begun reviewing them in preparation for issuing the necessary permits. Topic 2: Regulatory Correspondence & Strategic Support Two key letters were prepared: The first: An official response to the Saudi Business Center, appointing Mazen Al-Thunayan as the project representative. The second: A letter addressed to H.E. Yasir Al-Rumayyan titled "Overcoming Regulatory Challenges to Expedite NEOM Project Approvals", requesting support to convene a meeting with the Committee to approve a temporary mechanism for accelerating regulatory approvals. Topic 3: Jacobs Consultancy: Work has commenced with Jacobs on a 12-week consultancy project (ending in late November). This week: - The working group was formed. - A kick-off meeting was held. - The current project status is being assessed. Action Points: - Follow up on permit issuance by Riyadh Municipality. - Monitor progress of the Jacobs project and update the work plan based on the current state assessment.
125 | Demolishing App | Abdulrahman Algharib (SMP) | 2025-08-28 16:22 | Brief: Initial structuring and stakeholder engagement for the Demolishing App project has been completed, with PMO officially supporting the project across all stages. 1- Project Structuring – Phases and Roadmap: The project was structured into defined phases, and a comprehensive roadmap and execution plan were developed in coordination with the project manager. This structure will guide project delivery and tracking. 2- User Journey Design – Application Experience: A user experience map was designed to guide how users will interact with the Demolishing App. This ensures the solution is intuitive and aligned with operational requirements. 3- Stakeholder Alignment – Roles and Benefits: All relevant stakeholders and beneficiary parties were identified and briefed on their roles in the project. Their input will be critical for both implementation and ongoing system usage Action Points: 1- Continue PMO support across all phases. 2- Finalize documentation of roadmap and user journey. 3- Conduct next meeting to update and refine project planning.
128 | Seascape Counsil | Abdulrahman Algharib (SMP) | 2025-08-28 15:53 | On Hold due to restructuring across NEOM.
119 | Permits and Licenses Phase 2 | Abdulrahman Algharib (SMP) | 2025-08-18 08:55 | Brief: Over the past two weeks, several coordination meetings were held with internal and external stakeholders to advance regulatory efforts related to permitting and licensing across NEOM assets. Topic 1: Coordination with Riyadh Municipality – Nominated Consultants: On August 13, 2025 (corresponding to 19-02-1447H), NEOM received an official letter from Riyadh Municipality including a list of seven nominated consulting offices. These offices were proposed as part of the municipality’s support in facilitating regulatory engagement. Topic 2: Health Asset Licensing – Coordination with the Saudi Business Center: In collaboration with NEOM Health & Wellbeing, a list of assets including clinics and hospitals was submitted to the Saudi Business Center. The goal is to initiate the licensing process for these health facilities in alignment with national regulatory requirements. Topic3: Presentation and Formal Letter – Governance Challenges: A presentation has been prepared to be shared with the NEOM Board of Directors, following review by the Deputy CEO. The presentation highlights the current challenges NEOM is facing in complying with licensing requirements—primarily due to the absence of an approved Regional Plan. Alongside the presentation, a formal letter was drafted to be addressed to H.E. Yasir Al-Rumayyan, providing a detailed explanation of the governance and procedural barriers currently impacting permit issuance. The letter is under internal review prior to official submission. Action Points: 1- Finalize review and secure approval of the formal letter to H.E Yasir Al-Rumayyan. 2- Present the permitting challenges deck to the Deputy CEO, followed by NEOM Board. 3- Track progress on the licensing applications submitted to the Saudi Business Center.
125 | Demolishing App | Abdulrahman Algharib (SMP) | 2025-08-07 00:33 | Brief: Efforts are underway to strengthen the project's execution strategy and explore opportunities for internal development. Project Planning – Strategy & Execution Alignment: A one-on-one meeting was scheduled with the project manager to enhance the overall strategy and define a clear execution plan. The session will also focus on assessing user needs to ensure the application delivers optimal performance. In addition, a proposal will be discussed to collaborate with NEOM Tech & Digital for internal development of the application, reducing reliance on external vendors and ensuring better alignment with NEOM’s digital ecosystem. Action Points: Conduct the 1:1 session with the project manager.
128 | Seascape Counsil | Abdulrahman Algharib (SMP) | 2025-08-07 00:18 | Brief: The project is currently facing delays due to restructuring across NEOM. A follow-up meeting is scheduled to assess the way forward. Project Status – Pending Direction Amid Restructuring: Progress has been delayed due to the current restructuring. A meeting is scheduled on Wednesday with Paul from NEOM Nature to discuss whether a formal decision can be made or if the project should be put on hold until there is more clarity on roles and responsibilities. Action Points: 1- Attend the upcoming meeting with NEOM Nature. 2- Evaluate options to proceed or recommend putting the project on hold.
145 | Trasol Exctive Interface Appliction | Abdulrahman Algharib (SMP) | 2025-08-06 22:44 | Brief: The application is currently in the testing phase within the operational environment, with progress made on resolving initial technical observations. Trasol Executive Interface Application – Operational Testing & Integration Preparation: Over the past two weeks, the application underwent multiple functionality tests. Some issues were identified during testing—such as delays in login and inconsistencies in tracking incoming letters via email—which were reported and are currently being addressed in coordination with the developer. By Thursday, the application’s operational readiness was confirmed. The next steps include transitioning to electronic signature integration, led by NEOM Tech and Digital (Discussions Ongoing). Integration with the Nafath system is expected to take one week, followed by another week for testing. Additionally, coordination is ongoing with the Signet team for secure access integration. Action Points: 1- Complete resolution of technical feedback raised during the testing phase. 2- Proceed with Signet integration and electronic signature setup. 3- Finalize Nafath linkage and initiate end-to-end testing.
119 | Permits and Licenses Phase 2 | Abdulrahman Algharib (SMP) | 2025-07-29 10:35 | Brief Over the past two weeks, external and internal meetings were conducted to address NEOM’s permitting challenges and initiate licensing requirements for healthcare facilities. Topic 1 – External Meetings: Meetings were held following the official correspondence confirming that the Saudi Business Center has allocated a dedicated track for NEOM-related requests. Key challenges were identified to be raised to the Board of Directors, including the lack of approval for the regional and master plans. Topic 2 – Internal Meetings: Sessions with NEOM Health and Wellbeing focused on consolidating requests for licensing clinics and hospitals across NEOM. Collection of all licensing requirements has started in preparation for submission to the Saudi Business Center. Action Items: 1- Escalate identified challenges (regional and master plan approval) to the Board of Directors. 2- Finalize requirements for healthcare facility licensing and submit them to the Saudi Business Center to initiate the process.
145 | Trasol Exctive Interface Appliction | Kholoud Alhwaiti (SMP) | 2025-07-20 17:03 | Brief: The pilot phase of the application has been successfully completed, and preparations are now underway for the integration and official launch. Pilot Phase – Completed: The initial development and feature rollout were completed, followed by controlled pilot testing with executive users. The pilot phase concluded successfully on Saturday, confirming system readiness for broader deployment. Phase Two – Integration with Signet: The next phase focuses on integrating with the Signet authority to enable secure authentication and communication. Final launch preparations are in progress, with deployment planned for targeted executive users, including full functionality. Action Points: 1 - Initiate integration with Sign it for secure access protocols. 2- Finalize technical and user readiness for launch. 3 - Deploy the application to executive users with all features activated. 4 - Monitor performance and collect feedback post-launch.
125 | Demolishing App | Kholoud Alhwaiti (SMP) | 2025-07-16 16:24 | As of now, the project is still in its initial phase, and no new developments or activities
128 | Seascape Counsil | Abdulrahman Algharib (SMP) | 2025-07-16 16:07 | Brief: This week focused on the upcoming changes in the governance structure of NEOM’s marine oversight, with a key meeting planned to define the new approach. Upcoming Meeting with Nature – Seascape Governance Model: The original concept of establishing a Seascape Council is currently being reconsidered. Instead, a new governance model is being explored, which may involve the creation of a dedicated department rather than a council. A meeting is scheduled next week with Paul Marshall (Head of Nature) to discuss the proposed model, its structure, and how the initiative will move forward. The aim is to address current governance gaps and ensure a clear, agile, and compliant marine management structure aligned with NEOM’s long-term strategy. Action Points: 1- Attend the upcoming meeting with Nature to review the revised governance model. 2- Assess the implications of replacing the council with a new department. 3- Align internally on GA’s role in the proposed structure.
119 | Permits and Licenses Phase 2 | Abdulrahman Algharib (SMP) | 2025-07-10 12:12 | Brief: This week included strategic meetings with NEOM Municipality, Finance, Digital Government, and CDO-related teams to advance key elements of the Permits and Licenses project. Updates also include internal alignment with the CEO and progress tracking for the upcoming engagement with the selected consulting firm. TOPIC 1: Meeting with NEOM Municipality – Building Code: - A meeting was held with the NEOM Municipality team to review building code governance. It was proposed to amend the MoUs with MC and MOMH, consolidating all building code responsibilities under the MOMH MoU. - NEOM projects follow the Saudi Building Code as the main reference, with additional needs addressed by project teams in coordination with the relevant authorities. - An internal OCS committee was formed to compile currently used codes, identify gaps, and coordinate resolution efforts. A follow-up is recommended with MOMH, Riyadh Municipality, Civil Defense, and ETSD to agree on a clear implementation mechanism within NEOM. TOPIC 2: Meeting with NEOM Finance – Inherent Defects Insurance (IDI): A session with Nader (Chief of Finance) was held to discuss IDI. ExCom #374 (June 29) directed the following: - Full compliance with IDI regulations for buildings requiring occupancy certificates and permits. - Budget for required insurance. - Official letter to PIF requesting guidance. - Return to ExCom with detailed cost estimates. - Engage with external insurers to optimize costs. Formal communication and procurement updates are expected once these points are completed. TOPIC 3: Meeting with Digital Government –Automation of Permit Issuance Processes: The Digital Government team presented the system prototype. Work is ongoing to develop the internal user journey. Support will be requested from the EVP to finalize stakeholder engagement. TOPIC 4: Pending CDO Action – Consulting Firm Award: We are still awaiting confirmation from the CDO team on awarding the contract to the selected consulting firm. Once awarded, coordination will resume to align scope and next steps for implementation. TOPIC 5: Internal Meeting with the CEO – Project Presentation: A presentation summarizing the Permits and Licenses project and proposed next steps was delivered to the CEO. The key outcome of the meeting was an executive decision to send a formal letter to H.E. the Chair of the Supervisory Committee requesting support to expedite the opening of the One Stop Shop, in accordance with the Royal Decree. Action Points: 1- Coordinate with MOMH and external entities on building code implementation. 2- Follow up on the five IDI directives and prepare internal communication. 3- Finalize stakeholder identification for the licensing platform. 4- Follow up with the CDO team regarding the consulting firm award. 5- Support the CEO’s office in sending the letter to H.E. the Supervisory Committee Chair.
119 | Permits and Licenses Phase 2 | Abdulrahman Algharib (SMP) | 2025-07-02 17:12 | Brief: This week included key meetings with NEOM Codes and Standards and NEOM Projects to discuss recommendations related to the Permits and Licenses framework, specifically focusing on Recommendation 7 (Building Code) and Recommendations 8 & 9 (Licensing Platform). 1- Meeting with NEOM Codes and Standards (July 1): A meeting was held with NEOM Municipality, represented by the NEOM Codes and Standards team, to review the current status of Recommendation 7 regarding the application of the Building Code. During the discussion, a proposal was made to revise the current MoUs with both the Ministry of Commerce (MC) and the Ministry of Municipal and Rural Affairs and Housing (MOMH) by transferring all matters related to the Building Code to the MoU with the Ministry of Health (MOMH) It was clarified that all NEOM projects currently adopt the Saudi Building Code as the primary reference, with any additional requirements being addressed by the respective project teams in coordination with the relevant authorities. An internal committee has also been formed within OCS to collect the currently applied codes and identify any existing gaps. It is recommended to engage with MOMH to confirm the responsible entity following the code's transfer to the Center, and to organize a joint meeting with Riyadh Municipality, Civil Defense, and ETSD to establish a clear mechanism for code application in NEOM. 2- Meeting with NEOM Projects (July 2): A meeting was held with Faisal Alanzi from NEOM Projects to align on the Permitting and Licensing initiative from their perspective. It was agreed to schedule a follow-up meeting with NEOM Digital Government to present the first prototype of the licensing portal, which is referenced in Recommendations 8 and 9. Action Points: - Coordinate with MOMH to clarify the new responsible entity for the Building Code. - Arrange a joint meeting with Riyadh Municipality, Civil Defense, and ETSD to discuss code application in NEOM. - Finalize the internal review of existing codes and identified gaps within OCS. - Schedule and prepare for the prototype presentation meeting with NEOM Digital Government. - Continue alignment with NEOM Projects to ensure integration of perspectives and requirements.
128 | Seascape Counsil | Abdulrahman Algharib (SMP) | 2025-06-29 10:34 | Brief: The NEOM Seascape Council is in the final preparation phase ahead of its official activation. All foundational components—including charters, stakeholder alignment, and committee formation—have been completed. The project is now transitioning from setup to operational launch, pending the first council meeting. Key Topics: 1- Council & Committee Readiness: - Charters for the Council and all committees have been finalized and signed. - Five specialized committees are formed and ready to begin operations upon activation. 2- Stakeholder Engagement: - Alignment sessions have been conducted with all key internal sectors, including Nature Reserve, Water Mobility, Government Affairs, Environment, Public Safety, and the Port of NEOM. - Marine spatial plans and base regulations have been reviewed and updated in coordination with stakeholders.
128 | Seascape Counsil | Abdulrahman Algharib (SMP) | 2025-06-29 10:33 | Brief: The NEOM Seascape Council is in the final preparation phase ahead of its official activation. All foundational components—including charters, stakeholder alignment, and committee formation—have been completed. The project is now transitioning from setup to operational launch, pending the first council meeting. Key Topics: 1- Council & Committee Readiness: - Charters for the Council and all committees have been finalized and signed. - Five specialized committees are formed and ready to begin operations upon activation. 2- Stakeholder Engagement: - Alignment sessions have been conducted with all key internal sectors, including Nature Reserve, Water Mobility, Government Affairs, Environment, Public Safety, and the Port of NEOM. - Marine spatial plans and base regulations have been reviewed and updated in coordination with stakeholders.
119 | Permits and Licenses Phase 2 | Abdulrahman Algharib (SMP) | 2025-06-19 09:37 | Brief: Last 2 weeks, a meeting was held with the Municipality to review their internally developed system and asset list. Upon comparison, it became clear that there are significant discrepancies between their list and ours, which could directly impact the quality and reliability of the One Stop Shop. As a result, the data was analyzed and shared with the Projects Team for further review. 1- Asset List Alignment with Projects Team: The updated list was officially shared with the Projects Team, represented by Nawaf Al-Anzi and Syed, who are now revalidating the data with relevant stakeholders. This step aims to finalize a unified list that will serve as the basis for updating our internal system. 2- Permit-Related Collaboration Opportunity: During discussions with Nawaf, it was revealed that he has received internal directions to develop solutions for challenges related to building permits in NEOM projects. Given the overlap with our current initiative, the GA team has escalated this internally to explore effective collaboration opportunities—similar to the model established with Denis and the NPoW framework. 3- Engineering Consulting Company Selection: Based on the timeline shared by Denis’s team, the contract for the Engineering Consulting Company is expected to be awarded this week. Accordingly, we will reach out to them to confirm the final status and initiate coordination once the firm is officially appointed Action Points: - Await Projects Team’s feedback after reviewing the updated asset list. - Align with Nawaf’s team to explore integration opportunities related to building permit solutions. - Follow up with Denis’s team regarding the consulting firm selection and begin coordination. - Prepare for potential system updates once the final list is validated. - Continue internal coordination to ensure the One Stop Shop reflects accurate, unified asset data.
119 | Permits and Licenses Phase 2 | Abdulrahman Algharib (SMP) | 2025-06-19 09:32 | Brief: Last 2 weeks, a meeting was held with the Municipality to review their internally developed system and asset list. Upon comparison, it became clear that there are significant discrepancies between their list and ours, which could directly impact the quality and reliability of the One Stop Shop. As a result, the data was analyzed and shared with the Projects Team for further review. 1- Asset List Alignment with Projects Team: The updated list was officially shared with the Projects Team, represented by Nawaf Al-Anzi and Syed, who are now revalidating the data with relevant stakeholders. This step aims to finalize a unified list that will serve as the basis for updating our internal system. 2- Permit-Related Collaboration Opportunity: During discussions with Nawaf, it was revealed that he has received internal directions to develop solutions for challenges related to building permits in NEOM projects. Given the overlap with our current initiative, the GA team has escalated this internally to explore effective collaboration opportunities—similar to the model established with Denis and the NPoW framework. 3- Engineering Consulting Company Selection: Based on the timeline shared by Denis’s team, the contract for the Engineering Consulting Company is expected to be awarded this week. Accordingly, we will reach out to them to confirm the final status and initiate coordination once the firm is officially appointed Action Points: - Await Projects Team’s feedback after reviewing the updated asset list. - Align with Nawaf’s team to explore integration opportunities related to building permit solutions. - Follow up with Denis’s team regarding the consulting firm selection and begin coordination. - Prepare for potential system updates once the final list is validated. - Continue internal coordination to ensure the One Stop Shop reflects accurate, unified asset data.